## TASKS
Task ID | Task Name | Owner | Start Date | End Date | Status | Progress % | Priority | Estimated Hours | Actual Hours | Comments
1 | Planning | Alice | 2024-01-01 | 2024-01-09 | Completed | 100 | Medium | 52 | 43 | Testing phase
2 | Design | Bob | 2024-01-10 | 2024-01-31 | Completed | 100 | High | 94 | 87 | On track
3 | Development | Charlie | 2024-02-01 | 2024-03-14 | In Progress | 60 | Medium | 68 | 65 | Blocked
4 | Testing | Diana | 2024-03-15 | 2024-03-31 | Not Started | 0 | Low | 21 | 19 | On track
5 | Deployment | Edward | 2024-04-01 | 2024-04-05 | Not Started | 0 | High | 83 | 88 | Testing phase
6 | Requirement Gathering | Fiona | 2024-01-02 | 2024-01-08 | Completed | 100 | High | 58 | 50 | Completed successfully
7 | UI Design | George | 2024-01-05 | 2024-01-15 | Completed | 100 | Low | 41 | 39 | On track
8 | Backend Development | Alice | 2024-02-10 | 2024-03-20 | In Progress | 50 | Medium | 99 | 89 | Needs review
9 | Frontend Development | Bob | 2024-02-15 | 2024-03-25 | In Progress | 55 | Medium | 17 | 21 | Blocked
10 | Integration Testing | Charlie | 2024-03-17 | 2024-04-01 | Not Started | 0 | Low | 90 | 87 | On track
11 | Documentation | Diana | 2024-01-07 | 2024-01-17 | Completed | 100 | High | 33 | 41 | Completed successfully
12 | Code Review | Edward | 2024-02-20 | 2024-02-28 | Completed | 100 | Low | 89 | 86 | In progress
13 | API Development | Fiona | 2024-02-01 | 2024-03-05 | In Progress | 70 | Low | 66 | 56 | Blocked
14 | User Training | George | 2024-04-02 | 2024-04-15 | Not Started | 0 | Medium | 88 | 86 | Testing phase
15 | Bug Fixing | Alice | 2024-03-20 | 2024-04-10 | In Progress | 40 | Low | 21 | 18 | Needs review
16 | Performance Testing | Bob | 2024-03-25 | 2024-04-10 | Not Started | 0 | Low | 19 | 11 | Blocked
17 | Security Testing | Charlie | 2024-03-28 | 2024-04-12 | Not Started | 0 | High | 54 | 55 | On track
18 | Release Planning | Diana | 2024-04-05 | 2024-04-10 | Not Started | 0 | Medium | 29 | 19 | Completed successfully
19 | Environment Setup | Edward | 2024-01-01 | 2024-01-04 | Completed | 100 | High | 19 | 9 | On track
20 | Data Migration | Fiona | 2024-03-15 | 2024-04-05 | Not Started | 0 | Medium | 53 | 53 | On track
21 | Stakeholder Meeting | George | 2024-01-11 | 2024-01-11 | Completed | 100 | High | 88 | 78 | Completed successfully
22 | Risk Assessment | Alice | 2024-01-12 | 2024-01-20 | Completed | 100 | Medium | 50 | 48 | On track
23 | Test Case Preparation | Bob | 2024-02-25 | 2024-03-10 | In Progress | 60 | Low | 77 | 78 | Testing phase
24 | User Interface Testing | Charlie | 2024-03-16 | 2024-03-30 | Not Started | 0 | Low | 71 | 60 | Needs review
25 | Database Optimization | Diana | 2024-02-10 | 2024-02-28 | Completed | 100 | High | 23 | 25 | Blocked
26 | Load Testing | Edward | 2024-03-20 | 2024-04-04 | Not Started | 0 | Low | 93 | 88 | On track
27 | Software Installation | Fiona | 2024-01-05 | 2024-01-09 | Completed | 100 | High | 72 | 65 | Completed successfully
28 | Configuration | George | 2024-01-10 | 2024-01-15 | Completed | 100 | Medium | 29 | 27 | On track
29 | Customer Feedback | Alice | 2024-04-15 | 2024-04-25 | Not Started | 0 | Medium | 73 | 74 | Testing phase
30 | Regression Testing | Bob | 2024-03-28 | 2024-04-10 | Not Started | 0 | Low | 45 | 39 | Needs review
31 | Incident Management | Charlie | 2024-04-05 | 2024-04-20 | Not Started | 0 | Medium | 88 | 86 | On track
32 | Quality Assurance | Diana | 2024-01-15 | 2024-02-05 | Completed | 95 | High | 41 | 41 | Completed successfully
33 | Software Upgrade | Edward | 2024-04-01 | 2024-04-15 | Not Started | 0 | Low | 25 | 26 | Needs review
34 | Code Refactoring | Fiona | 2024-02-05 | 2024-02-20 | Completed | 100 | Medium | 36 | 30 | On track
35 | Project Handover | George | 2024-05-01 | 2024-05-10 | Not Started | 0 | High | 90 | 85 | Blocked
36 | Training Material Prep | Alice | 2024-03-12 | 2024-03-22 | In Progress | 50 | Low | 60 | 56 | Testing phase
37 | Budget Review | Bob | 2024-01-15 | 2024-01-20 | Completed | 100 | High | 45 | 44 | Completed successfully
38 | Security Patch | Charlie | 2024-02-15 | 2024-02-25 | Completed | 100 | High | 75 | 68 | On track
39 | Network Setup | Diana | 2024-01-02 | 2024-01-12 | Completed | 100 | Medium | 40 | 30 | Needs review
40 | Backup Configuration | Edward | 2024-01-14 | 2024-01-24 | Completed | 100 | Low | 38 | 31 | Completed successfully
41 | Change Management | Fiona | 2024-02-20 | 2024-03-05 | In Progress | 70 | Medium | 37 | 31 | Blocked
42 | SLA Definition | George | 2024-01-15 | 2024-01-25 | Completed | 100 | Low | 15 | 9 | On track
43 | Compliance Audit | Alice | 2024-03-01 | 2024-03-15 | Not Started | 0 | High | 44 | 48 | Needs review
44 | Incident Response | Bob | 2024-04-01 | 2024-04-10 | Not Started | 0 | Medium | 59 | 52 | On track
45 | User Acceptance Test | Charlie | 2024-04-12 | 2024-04-25 | Not Started | 0 | High | 23 | 20 | Blocked
46 | Project Planning Review | Diana | 2024-01-05 | 2024-01-10 | Completed | 100 | Medium | 32 | 31 | On track
47 | Cost Estimation | Edward | 2024-01-11 | 2024-01-20 | Completed | 100 | Medium | 33 | 34 | Completed successfully
48 | Data Analysis | Fiona | 2024-02-10 | 2024-02-25 | Completed | 90 | Medium | 47 | 43 | Testing phase
49 | Software Testing | George | 2024-03-20 | 2024-04-05 | Not Started | 0 | Low | 19 | 18 | On track
50 | System Integration | Alice | 2024-03-25 | 2024-04-12 | Not Started | 0 | High | 99 | 88 | Needs review
51 | Code Merge | Bob | 2024-02-10 | 2024-02-15 | Completed | 100 | Low | 27 | 20 | Completed successfully
52 | DevOps Pipeline Setup | Charlie | 2024-01-15 | 2024-02-01 | Completed | 100 | High | 55 | 45 | On track
53 | API Testing | Diana | 2024-03-05 | 2024-03-20 | In Progress | 55 | Medium | 80 | 70 | Blocked
54 | Database Backup | Edward | 2024-01-16 | 2024-01-20 | Completed | 100 | Low | 22 | 21 | Completed successfully
55 | Quality Control | Fiona | 2024-03-10 | 2024-03-25 | Not Started | 0 | Medium | 62 | 55 | Needs review
56 | Performance Tuning | George | 2024-03-28 | 2024-04-12 | Not Started | 0 | Low | 78 | 70 | On track
57 | Release Documentation | Alice | 2024-04-05 | 2024-04-12 | Not Started | 0 | Low | 42 | 39 | Blocked
58 | User Interface Update | Bob | 2024-01-20 | 2024-02-05 | Completed | 100 | Medium | 36 | 34 | On track
59 | Application Monitoring | Charlie | 2024-04-10 | 2024-04-25 | Not Started | 0 | Medium | 95 | 84 | Needs review
60 | Customer Support Setup | Diana | 2024-04-15 | 2024-04-30 | Not Started | 0 | Medium | 61 | 58 | Testing phase
61 | Endpoint Security | Edward | 2024-02-25 | 2024-03-05 | Completed | 100 | High | 18 | 15 | On track
62 | Feature Enhancement | Fiona | 2024-03-22 | 2024-04-05 | In Progress | 45 | Medium | 85 | 80 | Blocked
63 | Code Deployment | George | 2024-04-20 | 2024-04-25 | Not Started | 0 | Medium | 77 | 70 | Needs review
64 | Agile Sprint Planning | Alice | 2024-01-05 | 2024-01-10 | Completed | 100 | High | 23 | 21 | Completed successfully
65 | Security Review | Bob | 2024-04-01 | 2024-04-10 | Not Started | 0 | Medium | 58 | 55 | On track
66 | Database Migration | Charlie | 2024-02-15 | 2024-03-01 | Completed | 100 | High | 37 | 36 | Blocked
67 | Server Provisioning | Diana | 2024-01-12 | 2024-01-18 | Completed | 100 | Medium | 49 | 50 | On track
68 | Network Testing | Edward | 2024-02-20 | 2024-03-05 | Completed | 100 | Low | 27 | 26 | Completed successfully
69 | Backup Testing | Fiona | 2024-03-01 | 2024-03-10 | Completed | 100 | High | 51 | 49 | On track
70 | Release Notes | George | 2024-04-08 | 2024-04-12 | Not Started | 0 | Low | 59 | 56 | Needs review
71 | Risk Mitigation | Alice | 2024-01-20 | 2024-01-28 | Completed | 100 | High | 35 | 32 | On track
72 | Performance Monitoring | Bob | 2024-04-12 | 2024-04-25 | Not Started | 0 | Medium | 56 | 50 | Blocked
73 | Server Maintenance | Charlie | 2024-03-25 | 2024-04-05 | Not Started | 0 | Low | 44 | 40 | Needs review
74 | User Documentation | Diana | 2024-02-10 | 2024-02-20 | Completed | 100 | Medium | 38 | 35 | Completed successfully
75 | Code Debugging | Edward | 2024-03-15 | 2024-03-28 | In Progress | 50 | Low | 50 | 52 | Testing phase
76 | Training Session 1 | Fiona | 2024-04-15 | 2024-04-17 | Not Started | 0 | Low | 29 | 30 | On track
77 | Training Session 2 | George | 2024-04-20 | 2024-04-22 | Not Started | 0 | Low | 40 | 42 | Needs review
78 | System Audit | Alice | 2024-03-10 | 2024-03-20 | Completed | 100 | Medium | 33 | 31 | Completed successfully
79 | User Feedback Analysis | Bob | 2024-04-25 | 2024-05-05 | Not Started | 0 | Low | 34 | 36 | Blocked
80 | Post-Release Support | Charlie | 2024-05-10 | 2024-05-20 | Not Started | 0 | Medium | 40 | 41 | On track
81 | Vendor Coordination | Diana | 2024-01-12 | 2024-01-20 | Completed | 100 | Medium | 57 | 55 | Completed successfully
82 | Contract Review | Edward | 2024-01-25 | 2024-02-05 | Completed | 100 | Low | 62 | 60 | On track
83 | License Management | Fiona | 2024-02-10 | 2024-02-20 | Completed | 100 | Medium | 36 | 32 | Completed successfully
84 | Issue Tracking Setup | George | 2024-01-15 | 2024-01-25 | Completed | 100 | Low | 34 | 31 | On track
85 | Release Deployment | Alice | 2024-04-25 | 2024-04-30 | Not Started | 0 | Medium | 32 | 33 | Needs review
86 | Load Balancer Setup | Bob | 2024-02-10 | 2024-02-15 | Completed | 100 | Medium | 42 | 40 | Completed successfully
87 | Patch Management | Charlie | 2024-03-01 | 2024-03-10 | Completed | 100 | Medium | 36 | 35 | On track
88 | Security Training | Diana | 2024-04-10 | 2024-04-15 | Not Started | 0 | Low | 25 | 22 | On track
89 | Mobile App Testing | Edward | 2024-03-20 | 2024-03-30 | Not Started | 0 | Medium | 35 | 34 | Needs review
90 | User Interface Review | Fiona | 2024-02-25 | 2024-03-05 | Completed | 100 | Medium | 38 | 37 | Completed successfully
91 | Incident Reporting | George | 2024-04-01 | 2024-04-10 | Not Started | 0 | Low | 23 | 22 | Blocked
92 | Project Closure | Alice | 2024-05-15 | 2024-05-20 | Not Started | 0 | Medium | 40 | 38 | Needs review
93 | Asset Management | Bob | 2024-01-05 | 2024-01-15 | Completed | 100 | Low | 42 | 38 | On track
94 | Training Feedback | Charlie | 2024-04-25 | 2024-04-30 | Not Started | 0 | Low | 34 | 31 | On track
95 | Budget Adjustment | Diana | 2024-02-01 | 2024-02-10 | Completed | 100 | Medium | 45 | 44 | Completed successfully
96 | Incident Investigation | Edward | 2024-03-18 | 2024-03-25 | Not Started | 0 | Low | 38 | 36 | Needs review
97 | Software Licensing | Fiona | 2024-01-18 | 2024-01-28 | Completed | 100 | Medium | 41 | 40 | Completed successfully
98 | Deployment Verification | George | 2024-04-15 | 2024-04-20 | Not Started | 0 | Low | 35 | 33 | Blocked
99 | User Survey | Alice | 2024-04-20 | 2024-04-25 | Not Started | 0 | Medium | 30 | 29 | On track
100 | Backup Verification | Bob | 2024-02-20 | 2024-02-25 | Completed | 100 | Low | 33 | 30 | Completed successfully
101 | License Renewal | Charlie | 2024-04-01 | 2024-04-05 | Not Started | 0 | Medium | 40 | 38 | Needs review
102 | Security Audit | Diana | 2024-03-22 | 2024-03-30 | Not Started | 0 | High | 46 | 44 | On track
103 | System Upgrade | Edward | 2024-04-10 | 2024-04-20 | Not Started | 0 | Medium | 55 | 53 | Blocked
104 | Performance Review | Fiona | 2024-01-10 | 2024-01-15 | Completed | 100 | High | 22 | 20 | Completed successfully
105 | Team Meeting | George | 2024-01-20 | 2024-01-20 | Completed | 100 | Low | 18 | 17 | On track
106 | Risk Review | Alice | 2024-03-01 | 2024-03-05 | Not Started | 0 | Medium | 25 | 24 | Needs review
107 | Patch Testing | Bob | 2024-03-05 | 2024-03-15 | Not Started | 0 | Low | 35 | 33 | On track
108 | Documentation Update | Charlie | 2024-04-05 | 2024-04-10 | Not Started | 0 | Medium | 43 | 41 | Blocked
109 | Customer Support Setup | Diana | 2024-04-20 | 2024-04-30 | Not Started | 0 | Medium | 29 | 27 | Testing phase
110 | Server Security | Edward | 2024-02-10 | 2024-02-20 | Completed | 100 | High | 32 | 30 | Completed successfully
111 | Code Optimization | Fiona | 2024-03-15 | 2024-03-25 | In Progress | 60 | Medium | 38 | 36 | On track
112 | Client Presentation | George | 2024-01-10 | 2024-01-15 | Completed | 100 | Low | 22 | 20 | Completed successfully
113 | Bug Tracking | Alice | 2024-02-25 | 2024-03-10 | In Progress | 50 | Medium | 30 | 28 | Blocked
114 | System Backup | Bob | 2024-01-15 | 2024-01-20 | Completed | 100 | Low | 27 | 25 | On track
115 | Deployment Planning | Charlie | 2024-04-05 | 2024-04-10 | Not Started | 0 | Medium | 43 | 40 | Needs review
116 | Hardware Setup | Diana | 2024-01-01 | 2024-01-07 | Completed | 100 | High | 36 | 34 | Completed successfully
117 | User Training Prep | Edward | 2024-03-20 | 2024-04-05 | Not Started | 0 | Medium | 39 | 37 | On track
118 | Release Management | Fiona | 2024-04-01 | 2024-04-10 | Not Started | 0 | High | 50 | 48 | Blocked
119 | Status Reporting | George | 2024-01-05 | 2024-01-10 | Completed | 100 | Low | 30 | 28 | Completed successfully
120 | Final Review & Launch | Alice | 2024-05-10 | 2024-05-15 | Not Started | 0 | High | 58 | 57 | Needs review

## BUDGET
Category | Planned Budget | Actual Budget
Planning | 5000 | 4800
Design | 10000 | 10500
Development | 30000 | 28000
Testing | 8000 | 3000
Deployment | 7000 | 2000
Documentation | 3000 | 2500
User Training | 4000 | 0
Maintenance | 12000 | 5000
Risk Management | 2000 | 1000
Contingency | 5000 | 0
Communication | 2500 | 2000
Equipment | 7000 | 7000
Software Licenses | 9000 | 8500
Security | 4500 | 3000
Quality Assurance | 6000 | 4000
Infrastructure | 15000 | 12000
Vendor Management | 4000 | 3500
Support Services | 5000 | 4500
Marketing | 8000 | 5000
Legal & Compliance | 3000 | 3000

## RISKS
Risk ID | Risk Description | Impact | Likelihood | Mitigation Plan
101 | Requirement Changes | High | Medium | Implement change control
102 | Resource Shortage | Medium | High | Hire contractors
103 | Technical Issues | High | Medium | Frequent technical reviews
104 | Budget Overruns | High | High | Strict budget monitoring
105 | Schedule Delays | High | Medium | Agile project management
106 | Security Vulnerabilities | High | Low | Regular security audits
107 | Poor Communication | Medium | Medium | Establish clear channels
108 | Vendor Reliability | Medium | Medium | Select reliable vendors
109 | Technology Changes | Medium | Low | Continuous learning
110 | Market Changes | High | Low | Environmental scanning
111 | Compliance Issues | High | Low | Regular compliance checks
112 | Staff Turnover | Medium | Medium | Staff retention programs
113 | Data Loss | High | Low | Backup and recovery plans
114 | Inadequate Testing | High | Medium | Comprehensive testing plan
115 | Performance Bottlenecks | Medium | Medium | Performance tuning

## START DATE TIMELINE
Timeline: Works in Excel 2013 or higher. Do not move or resize.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## TIMELINES
Timeline: Works in Excel 2013 or higher. Do not move or resize.

## TIMELINE
Timeline: Works in Excel 2013 or higher. Do not move or resize.

## RISK MATRIX
Count of Risk ID | Column Labels
Row Labels | High | Medium | Grand Total
High | 1 | 1 | 2
Low | 4 | 1 | 5
Medium | 4 | 4 | 8
Grand Total | 9 | 6 | 15

## BUDGET SUMMARY
Row Labels | Sum of Planned Budget | Sum of Actual Budget
Communication | 2500 | 2000
Contingency | 5000 | 0
Deployment | 7000 | 2000
Design | 10000 | 10500
Development | 30000 | 28000
Documentation | 3000 | 2500
Equipment | 7000 | 7000
Infrastructure | 15000 | 12000
Legal & Compliance | 3000 | 3000
Maintenance | 12000 | 5000
Marketing | 8000 | 5000
Planning | 5000 | 4800
Quality Assurance | 6000 | 4000
Risk Management | 2000 | 1000
Security | 4500 | 3000
Software Licenses | 9000 | 8500
Support Services | 5000 | 4500
Testing | 8000 | 3000
User Training | 4000 | 0
Vendor Management | 4000 | 3500
Grand Total | 150000 | 109300

## ACTUAL HOURS
Row Labels | Sum of Actual Hours | Sum of Estimated Hours
Alice | 796 | 846
Bob | 693 | 746
Charlie | 872 | 936
Diana | 645 | 685
Edward | 726 | 758
Fiona | 755 | 821
George | 731 | 786
Grand Total | 5218 | 5578

## TASK PROGRESS
Row Labels | Average of Progress %
High | 67.6786
Low | 43.1707
Medium | 45.7843
Grand Total | 50

## TASK STATUS
Count of Task ID | Column Labels
Row Labels | Completed | In Progress | Not Started | Grand Total
Alice | 5 | 4 | 9 | 18
Bob | 8 | 2 | 7 | 17
Charlie | 4 | 1 | 12 | 17
Diana | 10 | 1 | 6 | 17
Edward | 9 | 1 | 7 | 17
Fiona | 9 | 4 | 4 | 17
George | 8 |  | 9 | 17
Grand Total | 53 | 13 | 54 | 120

## DASHBOARD
PROJECT MANAGEMENT DASHBOARD
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Recommendations:
1. Prioritize completing the Testing & Deployment phases on time.
2. Allocate more resources to the "Development" task (currently 60% complete).
3. Risks with High Impact & High Likelihood should be reviewed weekly.
Budget Notes:
1. Testing and Deployment are underutilizing their planned budgets.
2.Consider reallocating unused funds from Planning.